## Sheet1
TASK | DESCRIPTION | START DATE | DURATION | MAY | [19 empty] | JUNE | [20 empty] | JULY
|  |  |  | 7 | 8 | 9 | 12 | 13 | 14 | 15 | 16 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 2 | 3 | 4 | 5 | 6 | 9 | 10 | 11 | 12 | 13 | 16 | 17 | 18 | 19 | 20 | 23 | 24 | 25 | 26 | 27 | 30 | 1 | 2 | 3 | 4 | 7 | 8 | 9 | 10 | 11 | 14 | 15 | 16
TA1 | Study the PHIL lab documentation and hardware setup. | 2025-05-07 | 3 | bar: MAY 7 to MAY 9
TA2 | Explore the Matlab/Simulink models. | 2025-05-12 | 5 | bar: MAY 12 to MAY 16
TA3 | Test individual DG units and RTC integration. | 2025-05-19 | 8 | bar: MAY 19 to MAY 28
TB1 | Study the 5G module interface and configuration. | 2025-05-07 | 3 | bar: MAY 7 to MAY 9
TB2 | Test 5G network slice setup. | 2025-05-12 | 5 | bar: MAY 12 to MAY 16
TB3 | Defining the variables to be communicated using topics. | 2025-05-12 | 5 | bar: MAY 12 to MAY 16
TB4 | Test the 5G network setup after adding delay blocks. | 2025-05-19 | 8 | bar: MAY 19 to MAY 28
TC1 | Implement the frequency control scheme with delay blocks. | 2025-05-29 | 14 | bar: MAY 29 to JUNE 18
TC2 | Integrate communication and control systems. | 2025-05-29 | 14 | bar: MAY 29 to JUNE 18
TD1 | Evaluate system performance with and without delays in both simulation and hardware. | 2025-06-19 | 12 | bar: JUNE 19 to JULY 4
TD2 | Evaluate different topologies like Centralized, Decentralized and Distributed systems. | 2025-06-19 | 12 | bar: JUNE 19 to JULY 4
TD3 | Document setup, testing procedures, and findings. | 2025-07-07 | 3 | JULY 7: SK & LB
TD4 | Prepare final project report and presentation. | 2025-07-10 | 5 | JULY 10: SK & LB
Formulas:
START DATE = [START DATE, row above]+7
START DATE = [START DATE, row above]