## Slide 1: Grid Frequency Control with 5G Communication
Project Plan
Team Members: Santhosh Kumar (SK), Lubna Basha (LB)
Supervisors: Prof. Dr.-Ing. Johannes Schiffer, Dr. Rolando Cortes Martinez
Module: Laboratory Control and Network Control Technology, SoSe 2025

## Slide 2: Introduction
- Modern power systems face challenges with RES integration.
- Frequency control is key to grid stability.
- Traditional wired communication (Ethernet, fiber) limits scalability.
- 5G offers:
- Low latency
- High reliability
- Scalable device support

## Slide 3: Project Goal
- Use PHIL lab setup with distributed generators.
- Integrate 5G for frequency control.
- Compare performance of 5G vs. wired communication:
- Latency
- Reliability
- Responsiveness

## Slide 4: Subsystems Overview
Four key subsystems:
1. Subsystem A: PHIL Lab Familiarization
2. Subsystem B: 5G Communication Setup
3. Subsystem C: System Integration
4. Subsystem D: Testing & Analysis

## Slide 5: Subsystem A: PHIL Lab Familiarization
- Understand RTCs, DGs, and grid emulators.
- Learn Simulink control models.
- Basis for secure experimentation.

## Slide 6: Subsystem B: 5G Communication Setup
- Deploy 5G infrastructure in PHIL.
- Install modems and test latency, jitter, and speed.
- Enables low-latency wireless control.

## Slide 7: Subsystem C: System Integration
- Integrate PHIL and 5G components.
- Setup UDP communication.
- Implement and test frequency control logic.

## Slide 8: Subsystem D: Testing & Analysis
- Compare wired vs. 5G communication.
- Measure latency, stability, and reliability.
- Produce final evaluation report.

## Slide 9: Task Organization
- Subsystems A & B run in parallel.
- Subsystem C depends on A & B.
- Subsystem D depends on C.

## Slide 10: Working Plan - Task Durations
TA1 / TB1: 3 Days
TA2 / TB2 / TB3: 5 Days
TA3 / TB4: 8 Days
TC1: 6 Days
TC2: 8 Days
TD1 & TD2: 6 Days each
TD3: 3 Days
TD4: 5 Days